Tobacco Prevention for Specific Populations

Draft Critical Issues, Goals, and Strategies:  Timeline

| Goal: By June 30, 2010, all KS communities will have access to culturally and linguistically appropriate prevention and intervention resources for at least 4 specific populations. | June 07 | July-Sept 07 | Oct-Dec 07 | Jan-Mar 08 | Apr-June 08 | July-Sept 08 | Oct-Dec 08 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1)Identify population: Identify 4 populations |  |  |  |  |  |  |  |  |  |
| 1a)Evaluate & obtain data |  | X |  |  |  |  |  |  |  |
| 1b)Create process to identify specific populations in greatest need. |  |  | X |  |  |  |  |  |  |
| 2)Identify models: Identify potentially effective models and develop new models for existing gaps. |  |  |  |  |  |  |  |  |  |
| 2a)Research existing models. |  |  | X |  |  |  |  |  |  |
| 2b)Create directory of models. |  |  | X |  |  |  |  |  |  |
| 2c)Identify gaps. |  |  |  |  | X |  |  |  |  |
| 2d)Develop or modify models. |  |  |  |  | X |  |  |  |  |
| 3)Disseminate: Develop a community network to eliminate barriers by providing access to effective population-specific models. |  |  |  |  |  |  |  |  |  |
| 3a)Convene potential community partners. |  |  |  |  |  |  | X |  |  |
| 3b)Identify access barriers. |  |  |  |  |  |  | X |  |  |
| 3c)Develop web-based resource guide for population-specific prevention and intervention materials and techniques. |  |  |  |  |  |  |  | X |  |
| 3d)Market website and provide training. |  |  |  |  |  |  |  | X |  |
| 4)Evaluation: Evaluate dissemination process and network. |  |  |  |  |  |  |  |  | X |

| Goal: By June 30, 2009, there will be a functioning statewide strategy regarding collection, dissemination, integration and utilization of community-level quantitative and qualitative data to eliminate identified data gaps among specific populations. | June 07 | July-Sept 07 | Oct-Dec 07 | Jan-Mar 08 | Apr-June 08 | July-Sept 08 | Oct-Dec 08 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1)Conduct comprehensive assessments of available data to examine the range of factors related to tobacco use among disparately-affected populations. |  |  |  |  |  |  |  |  |  |
| 1a)Compile comprehensive sources of data in Kansas and nationally. |  |  |  |  |  |  |  |  |  |
| 1b)Create directory of available resources. |  |  |  |  |  |  |  |  |  |
| 1c)Complete report with relevant data to guide the strategic planning process and enrich disparities elimination efforts for tobacco control. |  |  |  |  |  |  |  |  |  |
| 1d)Print report. |  |  |  |  |  |  |  |  |  |
| 1e)Distribute report to key tobacco stakeholders and communities. |  |  |  |  |  |  |  |  |  |
| 2)Improve existing surveillance systems and suggest modifications or additions. |  |  |  |  |  |  |  |  |  |
| 2a)Catalog existing surveillance systems. |  |  |  |  |  |  |  |  |  |
| 2b)Access existing surveillance systems and suggest modifications or additions. |  |  |  |  |  |  |  |  |  |
| 2c)Identify specific minimum data set. |  |  |  |  |  |  |  |  |  |
| 2d)Define requirements for improvement of surveys, including cost requirements. |  |  |  |  |  |  |  |  |  |
| 2e)Identify funding sources. |  |  |  |  |  |  |  |  |  |
| 2f)Secure funding. |  |  |  |  |  |  |  |  |  |
| 2g)Finalize specifications. |  |  |  |  |  |  |  |  |  |
| 2h)Disseminate recommendations. |  |  |  |  |  |  |  |  |  |

| Goal: By June 30, 2009, there will be a functioning statewide strategy regarding collection, dissemination, integration and utilization of community-level quantitative and qualitative data to eliminate identified data gaps among specific populations. (cont.) | June 07 | July-Sept 07 | Oct-Dec 07 | Jan-Mar 08 | Apr-June 08 | July-Sept 08 | Oct-Dec 08 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3)Develop new data collection methods to access tobacco use where gaps in knowledge exist. |  |  |  |  |  |  |  |  |  |
| 3a)Create a data task force. |  |  |  |  |  |  |  |  |  |
| 3b)Review alternative sources of data, including qualitative data. |  |  |  |  |  |  |  |  |  |
| 3c)Create and test innovative data collection methods. |  |  |  |  |  |  |  |  |  |
| 3d)Implement, evaluate, share methods and new information. |  |  |  |  |  |  |  |  |  |
| 3e)Explore the possibilities for data collection and industry targeting. |  |  |  |  |  |  |  |  |  |
| 4)Disseminate available data to community key stakeholders. |  |  |  |  |  |  |  |  |  |
| 4a)Create a county community resource guide. |  |  |  |  |  |  |  |  |  |
| 4b)Use all available resources to disseminate information (print, electronic, media). |  |  |  |  |  |  |  |  |  |
| 4c)Communicate resources nationally. |  |  |  |  |  |  |  |  |  |
| 5)Link the data and data collection system with statewide and national tobacco prevention and cessation strategies. |  |  |  |  |  |  |  |  |  |
| 5a)Evaluate use of data collection systems. |  |  |  |  |  |  |  |  |  |
| 5b)Share information with national tobacco communities. |  |  |  |  |  |  |  |  |  |
| 5c)Make recommendations for future research. |  |  |  |  |  |  |  |  |  |
| 5d)Share data for utilization in health care curriculum. |  |  |  |  |  |  |  |  |  |
| 5e)Use data as a method for additional funding. |  |  |  |  |  |  |  |  |  |

| Goal: By June 30, 2010, educate and motivate communities, funders, and policymakers to support the elimination of tobacco-related health disparities in Kansas. | June 07 | July-Sept 07 | Oct-Dec 07 | Jan-Mar 08 | Apr-June 08 | July-Sept 08 | Oct-Dec 08 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1)By June 30, 2010, develop an integrated statewide advocacy plan to address tobacco-related health disparities. |  |  |  |  |  |  |  |  | X |
| 1a)Convene the advocacy action planning team – regional representatives, state and private partners. |  |  |  |  |  |  |  |  |  |
| 1b)Partner with local and state organizations to facilitate, train and provide data for advocacy action planning team. |  |  |  |  |  |  |  |  |  |
| 1c)Research and convene Cabinet members and legislative leaders regarding the advocacy action plan. |  |  |  |  |  |  |  |  |  |
| 2)By June 30, 2010, conduct a tobacco biannual training/meeting for communities, funders, and policymakers to support the elimination of tobacco disparities. |  |  |  |  |  |  |  |  | X |
| 2a)Identify and convene communities, funders, policymakers, and stakeholders. |  |  |  |  |  |  |  |  |  |
| 2b)Provide training for communities, funders, and policymakers regarding tobacco-related health disparities. |  |  |  |  |  |  |  |  |  |
| 2c)Evaluate the training/meeting of the above groups. |  |  |  |  |  |  |  |  |  |
| 3)By June 30, 2010, recruit and train a minimum of 5 sustainable community-based organizations per KDHE, TUPP (6) regions not previously involved in tobacco control work, in mobilization/implementation activities. |  |  |  |  |  |  |  |  | X |
| 3a)Develop and deploy a recruiting campaign for new specific-population groups (not involved in tobacco control). |  |  |  |  |  |  |  |  |  |
| 3b)Identify and recruit 5 community organizations for each region. |  |  |  |  |  |  |  |  |  |
| 3c)Train each community organization in Tobacco 101 and Best Practices. |  |  |  |  |  |  |  |  |  |
| 3d)Provide ongoing TA (online via website, evaluation). |  |  |  |  |  |  |  |  |  |
| 3e)Select a project to complete in each region (e.g., clean indoor air). |  |  |  |  |  |  |  |  |  |
| 3f)Evaluate the project (process, implementation) within each region. |  |  |  |  |  |  |  |  |  |