Tobacco Prevention for Specific Populations

Draft Critical Issues, Objectives, and Strategies

Updated: 6-28-07

Data

Critical Issue:  Increase community-level quantitative and qualitative data to eliminate identified data gaps among selected populations.

Objective:  By June 30 2009, there will be a functioning statewide strategy regarding collection, dissemination, integration, and utilization of community-level quantitative and qualitative data to eliminate identified data gaps among specific populations.

Strategies and Action Steps:

- Create a Data Action Team.

- Who:  Specific Populations Workgroup; Invitees:  Kansas Substance Abuse Profile Group, KU MPH Program, HK2010 Data Workgroup, Cancer Registry

- Target Date:  September 2007

- Resources:  KDHE (staff/logistics support) and community partners

- Conduct comprehensive assessments of available data to examine the range of factors related to tobacco use among disparately-affected populations.

  - Compile comprehensive sources of data in Kansas and nationally.

- Who:  KDHE – Tobacco Epidemiologist, Data Action Team

- Target Date:  Immediately.  By January 2008

- Resources:  Data access, human resources

  - Create directory of available resources.

- Who:  Data Action Team, TUPP Program Staff

- Target Date:  February 2008 and ongoing

- Resources:  Website for posting directory, human resources for updating

  - Complete report with relevant data to guide the strategic planning process and enrich disparities elimination efforts for tobacco control.

- Who:  Data Action Team, Tobacco Epidemiologist

- Target Date:  June 2008

- Resources:  Human resources; funding for printing or positing online

  - Coordinate distribution of report to key tobacco stakeholders and communities

- Who:  TUPP Media and Policy Coordinator; Specific Populations Marketing Action Team

- Target Date:  July 2008

- Resources:  Funding resources for production and distribution; seek funding resources

- Improve existing surveillance systems for data collection.

  - Catalog existing surveillance systems.

- Who:  Data Action Team

- Target Date:  February 2008

- Resources:  Funding resources for production and distribution; seek funding resources

  - Identify specific minimum data set.

- Who:  Data Action Team

- Target Date:  April 2008

- Resources:  Standard minimum data sets, surveillance system file layouts and definitions, human resources

  - Assess existing surveillance systems and suggest modifications or additions.

- Who:  Data Action Team

- Target Date:  June 2008 and ongoing

- Resources:  Data system access, human resources

  - Define requirements for improvement of surveys, including cost requirements.

- Who:  Data Action Team

- Target Date:  June 2008 and ongoing

- Resources:  Human resources, surveillance system data experts/representatives

  - Disseminate recommendations.

- Who:  Data Action Team

- When:  July 2008

- Resources:  Funding resources for distribution, as needed

  - Identify funding sources.

- Who:  Data Action Team

- Target Date:  August 2008

- Resources:  Human resources, knowledge of potential funding sources

  - Secure funding.

- Who:  Data Action Team

- Target Date:  February 2009

- Resources:  Human resources, grant writers

- Develop new data collection methods to assess tobacco use where gaps in knowledge exist.

  - Review alternative sources of data, including qualitative data.

- Who:  Data Action Team

- Target Date:  February 2008

- Resources:  Primary literature, human resources

  - Create and test innovative data collection methods

- Who:  Data Action Team, Tobacco Epidemiologist

- Target Date:  May 2008

- Resources:  Primary literature, human resources

  - Implement, evaluate, share methods and new information.

- Who:  Data Action Team

- Target Date:  June 2008 and ongoing

- Resources:  Primary literature, human resources

  - Explore the possibilities for data collection around industry targeting.

- Who:  Data Action Team

- Target Date:  August 2008

- Resources:  Human resources, primary literature

- Disseminate available data to community key stakeholders.

  - Create a county community resource guide.

- Who:  TUPP Program Staff, Data Action Team

- Target Date:  January 2009

- Resources:  Community data, website for posting directory, human resources for updating

  - Use all available resources to disseminate information (print, electronic, media) and communicate resources nationally.

- Who:  TUPP Media and Policy Coordinator, Marketing Action Team

- Target Date:  February 2009

- Resources:  Funding resources for printing (if applicable) and distribution

- Link the data and data collection system with statewide and national tobacco prevention and cessation strategies.

  - Evaluate use of data collection systems.

- Who:  Tobacco Epidemiologist, Data Action Team

- Target Date:  June 2008 and ongoing

- Resources:  Human resources, evaluation plan, data

  - Share information with national tobacco communities.

- Who:  TUPP Media and Policy Coordinator, Marketing Action Team

- Target Date:  July 2008 and ongoing

- Resources:  Funding for dissemination, human resources

  - Make recommendations for future research.

- Who:  Data Action Team

- Target Date:  July 2008 and ongoing

- Resources:  Literature, human resources

  - Share data for utilization in health care curriculum.

- Who:  Assessment Action Team

- Target Date:  July 2008 and ongoing

- Resources:  Data Action Team, data resources

  - Use data as method for additional funding.

- Who:  Assessment Action Team

- Target Date:  July 2008 and ongoing

- Resources:  Data Action Team, human resources

Specific Population Resources

Critical Issue:  Increase population-specific prevention and cessation resources that can be integrated in to community programs.

Objective:  By June 30, 2010, all KS communities will have access to culturally and linguistically appropriate prevention and cessation resources for at least 4 specific populations.

Strategies and Action Steps:

- Create an Intervention Action Team.

- Who:  Kansas Tobacco Prevention for Specific Populations Workgroup, TFKC, local health departments, TUPP, Center for Health Disparities, HK20101 Workgroup

- Target Date: October 2007

- Resources: KDHE Staff Support

- Identify four (4) specific populations based on current and evolving data.

  - Evaluate and obtain population-specific data.  Review data from Data Action Team.

- Who:  KDHE/Data Action Team

- Target Date: September 2007

- Resources: Human resources, time, data, data resources (BRFSS, Census data)

  - Create a process to identify specific populations in greatest need.

- Who:  TUPP, Office of Minority Health, Center for Health Disparities, Data Action Team, Safety Net Clinics

- Target Date: December 2007

- Resources: Human resources, local health departments, FQHCs, Center for Health Disparities

- Identify potentially effective models and develop new models for existing gaps.

  - Research existing models.

- Who:  KDHE/TUPP, KU Med

- Target Date: December 2007

- Resources: CDC, web sites, CDC Best Practices book, Cancer Control, American Lung Association, American Heart Association, American Cancer Society, TFKC, Cancer Information Service

  - Create directory of models.

- Who:  KDHE

- Target Date: February 2008 (to be completed simultaneously with research step); January 2008

- Resources: CDC, web sites, Best Practices book, Cancer Control, American Lung Association matrix of models

  - Identify gaps.  Use data from Data Action Team.

- Who:  Intervention Action Team: KS Substance Abuse Profile Group, KU MPH, HK2010 Data Workgroup, Cancer Registry

- Target Date:  June 2008

- Resources: Data.  Other resources same as above (CDC, web sites, Best Practices book, Cancer Control, Lung Association).  Create links to other websites.

  - Develop or modify models.

- Who:  Intervention Action Team and TUPP

- Target Date: August 2008

- Resources: Data.  Other resources same as above (CDC, web sites, Best Practices book, Cancer Control, Lung Association)

- Develop a community network to eliminate barriers by providing access to effective population-specific models.

  - Convene potential community partners.

- Who:  KDHE/TUPP, Center for Health Disparities, Coordinated School Health, Regional Prevention Centers

- Target Date: December 2008

- Resources: Meeting location, facilitator, incentives, funding

    - Identify access barriers.

- Who:  Intervention Action Team and Community Partners

- Target Date: December 2008

- Resources: Meeting location, facilitator, incentives, funding, CDC, internet, best practices, human resources

  - Develop Web-based resource guide for population-specific prevention and intervention materials and techniques.

- Who:  KDHE/TUPP

- Target Date: June 2009

- Resources: I.T., funding, website, human resources

  - Market Web site and provide training.

- Who:  KDHE/TUPP

- Target Date: December 2009

- Resources: I.T., funding, website, human resources, Community Health Centers

- Evaluate dissemination process and network.

- Who:  KDHE, TUPP, Assessment Action Team

- Target Date: June 2010

- Resources: Staff, data analysis, access to report from agencies

- Questions:

      - What data tools will be used to collect this information?

      - What data is most useful for the community?

Advocacy and Policy

Critical Issue:  Increase advocacy for the elimination of tobacco-related health disparities among specific populations in Kansas.

Objective: By June 30, 2010, conduct a campaign to educate and motivate communities, funders, and policymakers to support the elimination of tobacco-related health disparities among specific populations  in Kansas.

Strategies and Action Steps:

- Develop an integrated statewide advocacy plan to address tobacco-related prevention and cessation issues for specific populations.

  - Create an Advocacy Action Team.

- Who:  KDHE/TUPP;  Members may include:  KS Tobacco Prevention for Specific Populations Workgroup, regional representatives, state and private partners

- Target Date:  September 2007

- Resources:  KDHE support staff; human resources

  - Convene the Advocacy Action Team

- Who:  TUPP staff, TFKC, and partners

- Target Date: Yearly, to begin in January 2008

- Resources: Trainers, locations, materials, collaborate with partners (heart, lung, cancer; state and private), Comprehensive Cancer Control Plan

  - Partner with local and state organizations to facilitate, train, and provide data for Advocacy Action Team.

- Who:  TUPP, TFKC

- Target Date: Yearly, to begin in February 2008

- Resources: Trainers, locations, materials, partners

  - Reach and convene the Cabinet members and legislative leaders regarding the advocacy action plan.

- Who:  TFKC and other partners

- Target Date:  Biannual, to begin in March 2008

- Resources:  Coalitions, TUPP, TFKC

- Conduct a tobacco biannual training/meeting for communities, funders, and policymakers to support the elimination of tobacco disparities.

  - Identify and convene communities, funders, policy makers, and stakeholders.

- Who:  Local Coalition (6 TUPP Regions)

- Target Date: Yearly, to begin in Spring 2008

- Resources: Trainers, location, materials, collaborate with existing partners (state and private), Coordinated School Health

  - Provide training for communities, funders, and policymakers regarding tobacco-related health disparities.

- Who:  TUPP, TFKC, KPHA, other community partners

- Target Date:  Yearly, to begin in Spring 2008

- Resources:  Human resources, funding, locations, materials, partners

  - Evaluate the training/meeting of the above groups.

- Who:  KDHE/TUPP

- Target Date:  Immediately after each training

- Resources:  Human resources, funding, KDHE Tobacco Epidemiologist

- Recruit and train a minimum of five (5) sustainable community-based organizations per KDHE, TUPP (6) regions not previously involved in tobacco control work, in mobilization/implementation activities.

  - Develop and deploy a recruiting campaign for new specific-population groups (not involved in tobacco).

- Who:  TUPP

- Target Date: To begin in March 2008, and then ongoing

- Resources: Marketing, materials, health departments

  - Identify and recruit 5 community organizations for each region.

- Who:  Advocacy Action Team; TUPP

- Target Date:  March 2008

- Resources:  Human resources, print materials

  - Train each community organization in Tobacco 101 and Best Practices.

- Who:  KDHE/TUPP

- Target Date:  April 2008

- Resources:  Human resources, training

  - Provide ongoing TA (online via Web site-site).

- Who:  KDHE/TUPP

- Target Date:  To begin in April 2008, and then ongoing

- Resources:  Web resources

  - Select a project to complete in each region (e.g., clean indoor air).

- Who:  Community organizations

- Target Date:  To begin in April 2008

- Resources:  Funding; KDHE/TUPP technical assistance

  - Evaluate the project (process, implementation) within each region.

- Who:  TUPP

- Target Date: Ongoing

- Resources: Workgroup for Specific Populations, TUPP, health departments, coalitions